## Project Planner
CPSC Senior Project: F. Kato
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 15 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project selection | 1 | 3 | 1 | 0 | 100%
Abstract - initial | 2 | 3 | 1 | 2 | 100%
Abstract - Final | 4 | 2 | 4 | 1 | 100%
Project Design | 2 | 5 | 2 | 5 | 100%
Project coding | 4 | 8 | 4 | 10 | 100%
Project testing | 9 | 5 | 11 | 4 | 100%
Project Demo Preparation | 8 | 2 | 8 | 0 | 100%
User Interface Selection | 2 | 2 | 2 | 2 | 100%
UI Design | 3 | 2 | 3 | 2 | 100%
UI Coding | 6 | 4 | 6 | 6 | 100%
Data Storage Selection | 2 | 2 | 2 | 2 | 100%
Data Storage Design | 3 | 3 | 3 | 8 | 100%
Data Storage Coding | 4 | 6 | 5 | 7 | 100%
Design Program 1 | 3 | 2 | 3 | 2 | 100%
Code Program 1 | 6 | 7 | 6 | 6 | 100%
Test Program 1 | 9 | 4 | 12 | 3 | 100%
Design Program 2 | 9 | 2 | 10 | 1 | 100%
Code Program 2 | 9 | 5 | 11 | 13 | 100%
Test Program 2 | 11 | 1 | 11 | 3 | 100%
Design Program - other | 3 | 3 | 0 | 0 | 0%
Code Program - other | 5 | 7 | 0 | 0 | 0%
Test Program - other | 9 | 4 | 0 | 0 | 0%
System Documentation | 11 | 4 | 11 | 3 | 100%
Algorithm Analysis | 11 | 2 | 10 | 1 | 100%
Deliverables Folder | 14 | 1 | 14 | 1 | 100%
Presentation Preparation | 13 | 2 | 13 | 2 | 100%

## Sheet1
Project selection
Abstract - initial
Abstract - Final
Project Design
Project coding
Project testing
Project Demo Preparation
User Interface Selection
UI Design
UI Coding
Data Storage Selection
Data Storage Design
Data Storage Coding
Design Program 1
Code Program 1
Test Program 1
Design Program 2
Code Program 2
Test Program 2
Design Program - other
Code Program - other
Test Program - other
Deliverables Folder
Algorithm Analysis
System Documentation